## Requirements
Time Track Details
S.No. | Task/Issue | Assigned To | Status | Comments | Expected Time
1 | Please make sure the numeric values have 2 decimal points (00.00) |  | Done | As per Raju, minutes are not needed.
2 | The Total should automatically sum up the hours for the week with 2 decimal points (00.00) |  | Done | Currently, total is summing up the hours, but with no decimal point.
3 | The business rule that roled to next week is based on Time. |  | Done | All weeks in the current month are displayed.
4 | If the Total hours are less than 40 hours then highlight yellow. If the Total hours are greater than 40 hours then highlight red. |  | Done |  | Done
5 | Populate Previous submitted hours from previous weeks. Allow user to make changes to previous submitted hours. |  | Done | Displayed only for the current month.
6 | SMS reminder sent to employee |  | On Hold
7 | Please add an option to have a CSV download option. Would like to extract it onto an excel spreadsheet | Harini | Done | Provided in the 'Day' tab. Need to work on 'Week' tab. 'Download' option provided in the 'Week' tab.
8 | Default week set to the Monday of the current week |  | Done | Monday to Friday is displayed for normal users. Sunday to Saturday for Admins.
9 | Replace "Number of Weeks" with a date range option in the 'Week' tab. | Harini | In Progress | Display Welcome message for all users. All weeks in the current month are displayed for normal user. For Admin, the 'From' and 'to' dates should appear.
10 | Link to TriNet profile (TriNet Employee Number - Employee Last Name, First Name) |  | On Hold
11 | View date of last update |  | Clarification needed | Currently, this is captured in database and downloaded excel file. Is it required to be displayed on the UI?
12 | If multiple weeks selected, they will appear in separate rows |  | Done | All weeks in the current month are displayed. Each week is displayed on a separate row.
13 | Admins will have the right to update specific fields |  | Done
14 | Provide an Audit trail on when and by whom changes have occurred | Sunil | Done | Tables created in DB | 28/06/2016
15 | Provide "Sum" of all hours |  | Done | Implemented in 'Week' tab.
16 | Reminder emails to employees who have not submitted activity log | Harini | Done | Working fine. Mail server issue is resolved. Coding is done. Mail server is not working. Need to follow up to get it resolved. Please send an email to resource on Monday morning, and to the resource and timetracker@italentcorp.com on Monday evening.
17 | When click on edit in day tab, highlight the hours / task desc fields. | Sunil | Done | Highlighted the 'Task Details' field on edit.
18 | Week tab should be first then day tab | Harini | Done
19 | User name also need to add for normal user in week tab | Harini | Done
30 | On reports, we need to add everyone's iTalent Number and country. US iTalent number is their TriNet number. India iTalent number is the same number that is on their badge. | Sunil/Harini | In Progress | Change the excel report name to "TimeTracker_<tab name>_<username>". Ex: TimeTracker_Week_AllUsers Columns added in iConnect and database. Logic to save these fields into database is in progress. Sunil to add iTalent number in iConnect. Columns order should be Emp No,user name,email id,country,pro name,date,hours,desc,updated date | 29/6/2016
31 | We need Saturday and Sunday added to the weekly and daily calendars | Harini | Done
32 | Reference Documents explaining how to log daily and weekly hours | Srujana / Karen | Yet to Start
33 | Zeros need to be yellow on reporting documents | Harini | Done
34 | A Scrollable table to see who has reported their hours. Tu emailed example | Narisi/Sunil | In Progress | Hide the 'Save' column when 'All Users', 'India Users', 'US Users' is selected from the drop-down. Display only 4 weeks data. If the data between date ranges > 4 weeks, display alert to force user to download report. Also seggregate 'All users', 'USA users', 'India Users'. | 30/6/2016

## Issues
Time Track: Work status
Date : | June 7th 2016 | Prepared By: | Sunil
Time Track Details
Track# | Task/Issue | Steps to reproduce | Assigned To | Status | Comments | Expected Time
1 | Unable to submit effort in 'Day' tab. 'Submit' button is disabled. | Go to the day tab in time track, Enter values trying to click on submit button as disabled state | Chinni | Done
2 | Unable to edit effort as 'Submit' button is disabled. | Go to the day tab in time track, select exiting time track. Showing submit button as disabled state | Chinni | Done
3 | When the 'Delete' icon is clicked against any record, there is not alert/warning to the user to confirm deletion. The record is deleted. This is problem in case of accidental deletions. | Go to the day tab in time track, click on delete icon for exiting time track. | Harini | Done
4 | Under 'List of Task Updates', entered the 'From' date as 2016-06-01 and 'To' date as 2016-05-29. This should not be allowed. To date cannot be less than from date. No alert displayed. | Go to the day tab in time track. Select From date and "To date" for filter | Chinni | Done | Disabling "Go" button when To date greater than from date | 2016-06-13
5 | Even when the above values are reversed, no rows are returned (there are 2 records in that date range). | Go to the day tab in time track. Select "From date" and "To date" for filter | Chinni | Done
6 | In case of zero records fetched, the 'Download Data' button should be disabled. | Go to the day tab in time track. Click on download data without data | Harini | Done
7 | There is no option to 'Clear' the date fields. | Go to the day tab in time track. Select "From date" and "To date" for filter | Harini | Not done | Taking as low priority.
8 | The 'Search' bar functionality is not working. | Go to the day tab in time track. Find the search bar enter the text | Sunil | Done | Tested working fine now
9 | After effort is entered and saved in 'Week' tab, this effort is not reflected in the 'Day' tab under 'List of Task Updates'. There is no 'Refresh' button either. Had to refresh the whole page to see the updated details. | Go to week tab in time track. Enter the values in day text boxes and save. Goto day tab check the week data | Chinni | Done | populating the data when save in week tab
10 | Need to hide the Saturday and Sunday columns to normal user. | Go to the week tab in time track. Need to hide the Saturday and Sunday columns to normal user. | Chinni | Done
11 | Users list should be in week tab. Should be visible to admin | Go to the week tab in time track. Users list should be in week tab. Users drop down should be visible to admin | Chinni | Done |  | 2016-06-13
12 | When enter the value in text boxes hours should be allow <= 24 hrs | Go to the week tab in time track. When enter the value in text boxes hours should be allow <= 24 hrs | Harini | Done | Now showing default alert need to change it to custom alerts message | 2016-06-14
13 | Between dates not working fine | When select the same dates in from and to dates not working fine | Narsi | Done
13 | Normal user UI showing when admin user delete the working details | Go to the day tab in time track as admin login it shows the admin user UI. Try to delete the record. Then loading normal user UI | Chinni | Done |  | 2016-06-13
14 | When try to delete the selected work detail, it deleting other work detail in day tab | Go to day tab--> Delete any work detail, always deleting first record | Chinni | Done | Now showing default alert need to change it to custom alerts message | 2016-06-13
15 | When admin user edit the normal user's data, then update it as login user's userID |  | Harini | Done |  | 2016-06-13
16 | On Admin login when try to delete the project without select giving confirmation alert instead of check the project selection | Go to the day tab in time track as admin login. Click on Delete Project button without select the project. | Chinni | Done |  | 2016-06-13
17 | On normal user login after save the week details day tab work details are loading for all users. | Go to week tab save work hours and click on day tab it show all users details | Chinni | Done |  | 2016-06-13
18 | Saving project name without any text in project input box | Go to the day tab in time track as admin login. Click on Add Project | Chinni | Done | It should give the alert when text box is empty | 2016-06-14
19 | In Day tab with normal user login when delete the work details. Not refreshing the grid with data |  | Chinni | Done |  | 2016-06-14
20 | When enter the value >24 in text boxes, should give the alert in the save button |  | Harini | done | While enter the value getting alert but In save button click also need to show the alert | 2016-06-15
21 | For project save button shold be change the name as "Save" instead of "Go" |  | Harini | Done |  | 2016-06-14
22 | Place hold need to add for praject name input box on new project saving |  | Harini | Done |  | 2016-06-14
23 | Remove the do in Are sure do you want to delete in both tabs |  | Harini | Done |  | 2016-06-16
24 | Dowload data is not working properly, downlaoding only first page |  | Chinni | Done |  | 2016-06-16
25 | Even To date less than From date dowload data button should be disable or not allow the date to select the lesser |  | Harini | Done |  | 2016-06-16
26 | When delete the record loading all records irrespective of date selection |  | Chinni | Done |  | 2016-06-16
27 | When click save project without text showing different message in second click |  | Chinni | Done |  | 2016-06-16
28 | When click on go button after the load page, records disappearing. |  | Chinni | Done |  | 2016-06-16
29 | When click submit button need to show the alert |  | Narsi | Done
30 | Allowing 'e', 'E', '-' characters in the effort fields in 'Week' tab. |  | Harini | Done